## UAT Checklist
Role: Guard |  | Generated: February 18, 2026 |  | Tester fills one of Approved/Partial/Not Done per test
Test ID | Module | Scenario | Steps | Expected Result | Approved | Partial | Not Done | Comments
GU-001 | Authentication | Valid OTP login | Open app, enter valid mobile, send OTP, enter OTP, login. | User logs in and reaches correct role dashboard.
GU-002 | Authentication | Invalid OTP handling | Enter incorrect OTP and submit. | Login is blocked with clear validation message.
GU-003 | Authentication | Tenant selection flow | Select tenant when prompted after login. | Chosen tenant is applied and dashboard opens.
GU-004 | Session | Session persistence | Close app and reopen without logout. | User session restores correctly unless token expired.
GU-005 | Dashboard UI | Header title and bell visibility | Open dashboard and inspect top header. | Role title and notification bell are visible and aligned.
GU-006 | Dashboard UI | Greeting card layout | Inspect greeting card in portrait mode. | Name, greeting, and logo area render without clipping.
GU-007 | Dashboard UI | Logo fallback behavior | Use account with missing logo URL. | Fallback branding or placeholder shows without broken UI.
GU-008 | Dashboard UI | Quick action tile readability | Inspect tile labels/icons on normal and small display. | Labels are readable and icons not cut off.
GU-009 | Dashboard UX | Tile tap responsiveness | Tap each tile once. | Tap feedback is immediate and correct screen opens.
GU-010 | Dashboard UX | Pull-to-refresh | Pull down on dashboard. | Refresh indicator appears and data updates.
GU-011 | Notifications | Open notifications list | Tap bell icon from dashboard. | Notifications screen opens successfully.
GU-012 | Notifications | Back navigation from notifications | Open notifications then tap back. | Returns to previous dashboard without state loss.
GU-013 | Comm Box | Open comm box module | Tap Comm Box tile if available. | Comm Box opens with list or empty state message.
GU-014 | Comm Box | Open communication detail | Tap any communication item. | Detail view/modal opens with readable content.
GU-015 | Error Handling | Offline/weak network behavior | Disable network and open data-heavy screen. | App shows non-crashing error or empty state with retry guidance.
GU-016 | Navigation | Back-stack consistency | Navigate Dashboard -> module -> detail -> back repeatedly. | Back action always returns expected previous screen.
GU-017 | UX | No overlap on long names | Use account with long name and open dashboard/profile. | Text wraps/truncates cleanly without overlap.
GU-018 | Performance | List rendering smoothness | Scroll through long list in any module. | Scrolling is usable and no severe lag/freezing.
GU-019 | Profile | Open profile screen | Tap Profile tile. | Profile data screen opens correctly.
GU-020 | Profile | Logout flow | Tap Logout and confirm. | User returns to login/tenant flow and session clears.
GU-021 | QR | Open QR scanner screen | Tap QR Code tile. | Scanner/manual lookup screen opens.
GU-022 | Checklist | Open guard checklist | Tap Checklist tile. | Guard checklist list loads.
GU-023 | Checklist | Task completion with evidence | Complete one task requiring comment/photo. | Task completes and evidence is retained.
GU-024 | Checklist | Checklist submit validation | Try submit before all required tasks done. | Submit is blocked with instruction.
GU-025 | Checklist | Submit checklist success | Complete all required tasks and submit. | Checklist submission succeeds.
GU-026 | Leave | Leave list visibility | Open Leave tile. | Leave requests list loads with status badges.
GU-027 | Outpass | Outpass list visibility | Open Outpass tile. | Outpass requests list loads with status badges.
GU-028 | Guest Entry | Guest entry list visibility | Open Guest Entry tile. | Guest entry list loads with status badges.
GU-029 | Outpass | Outpass verification action availability | Open approved and non-approved records. | Verification action appears only when allowed.
GU-030 | Outpass | Mark outpass verification | Run verification on approved outpass. | Request moves to completed/verified state.
GU-031 | Guest Entry | Mark guest entry verification | Run mark entry on approved guest request. | Request transitions to completed entry state.
GU-032 | History | Open guard history tabs | Open Profile -> History and switch tabs. | Leave/Outpass/Guest completed histories load.
GU-033 | Comm Box | Read comm item | Open Comm Box and open a message. | Message detail is readable.
GU-034 | Operational Flow | Guard shift E2E | Checklist + one movement verification + history review + logout. | Shift flow completes without blockers.
GU-035 | UI/UX | Consistent spacing and alignment | Inspect cards, headers, filters, and list rows across 3+ screens. | No major misalignment, overlap, or clipped content.
GU-036 | UI/UX | Color contrast and legibility | Inspect text on colored badges/buttons and cards. | Critical labels and actions are readable in normal lighting.
GU-037 | UI/UX | Touch target comfort | Tap small chips/icons (filters, close buttons, back arrow). | Targets are usable without repeated accidental taps.
GU-038 | UI/UX | Empty state communication quality | Open module with no data. | Empty state explains what is missing and next action clearly.
GU-039 | Reliability | API error feedback quality | Force API failure case and perform action. | User sees clean error message without raw stack trace.
GU-040 | Reliability | Screen crash check | Rapidly navigate between dashboard and modules 10+ times. | No crash, freeze, or broken navigation state.